## UAT Checklist
UAT ID | Related BRS | Business Need (Plain Language) | Acceptance Question | Evidence / Where to Look | Sign-off
UAT-001 | BRS-001 | Customers should be able to open and manage their own bank accounts without needing a teller for every routine action. | Can a customer submit a new account request, and later view their own account details themselves, without staff help? | FT-001 (account request), FT-005 (self-service view) -- both Executed-Pass in functional_test_cases.xlsx | Pending
UAT-002 | BRS-002 | Customers should be able to use a self-service ATM channel to withdraw cash, check their balance, and manage their PIN. | Can a customer log in at the ATM with their account number and PIN, withdraw cash, check their balance, and change their PIN? | FT-006, FT-007, FT-009, FT-010 -- all Executed-Pass in functional_test_cases.xlsx | Pending
UAT-003 | BRS-003 | Bank staff should be able to review and approve or decline new account applications before they become active. | Can an administrator log in, see pending account requests, and approve or decline them -- with declined/approved accounts behaving correctly afterward? | FT-003, FT-004, FT-014, FT-015 -- all Executed-Pass in functional_test_cases.xlsx | Pending
UAT-004 | BRS-004 | Customers should be able to submit utility bill payments through the bank, to be processed by staff. | Can a customer submit a bill payment request, and can staff see and process it afterward? | FT-011 -- Executed-Pass in functional_test_cases.xlsx | Pending
UAT-005 | BRS-005 | The bank needs an internal way to queue and process cash withdrawal and deposit requests in the order they were received. | If a customer submits a deposit or withdrawal request, does it get processed in order, and does it correctly update the customer's balance? | FT-008 -- Executed-Pass in functional_test_cases.xlsx | Pending
UAT-006 | BRS-006 | Sensitive customer data (PINs, passwords) should be protected from inappropriate exposure. | Does the system reject clearly invalid PINs, and does it avoid displaying stored passwords back to the user unnecessarily? | UT-023, UT-093, UT-094 (PIN validation); SRS-024/SRS-027 noted as Partial coverage in traceability/RTM.xlsx -- see Coverage Summary for detail | Pending
UAT-007 | BRS-007 | The system should be rebuilt as a modular, portable, maintainable C codebase, suitable for long-term ownership. | Is the codebase organized into clear, independent modules; does it build and pass its full test suite on a standard Windows development machine; and does the CI pipeline run it successfully on every push? | docs/design/HLD.md (module breakdown), 100/100 unit tests passing, 15/15 functional tests passing, CI pipeline green on GitHub Actions | Pending

## Legend
Legend / How to Use This Checklist
Purpose:
- User Acceptance Testing (UAT) is the final, simplest check in the
V-Model: does the finished system actually satisfy the original
business need stated in BRS, in plain language a non-technical
stakeholder can understand and sign off on?
How this differs from Functional Testing:
- Functional tests (functional_test_cases.xlsx) verify exact technical
steps and outputs (e.g. 'balance becomes 300.00').
- UAT verifies the business outcome in everyday language (e.g. 'can a
customer withdraw cash at the ATM?'), and points to the functional/
unit test evidence that already proves it, rather than re-testing.
Columns:
- UAT ID: UAT-001, UAT-002, ... one row per BRS item.
- Business Need: restates the BRS requirement in plain language.
- Acceptance Question: the yes/no question a business stakeholder
would actually ask.
- Evidence: which existing test artifacts already answer the
question, so UAT re-uses proof rather than duplicating effort.
- Sign-off: Pending ¦ Accepted ¦ Rejected. To be completed by a
project owner or business stakeholder reviewing the evidence.
Note on UAT-006 and UAT-007:
- These reference 'Partial' coverage items already disclosed in
traceability/RTM.xlsx. UAT does not hide or resolve those gaps --
it surfaces them plainly so a business stakeholder can decide
whether the current level of verification is acceptable to sign
off on, or whether further test coverage should be requested
before acceptance.